## OVERVIEW
Tracker Item | Current Status | What This Means | Next Action | Evidence
Purpose | New tracker based on current implementation | Use this for thesis rewrite, QA defense prep, and feature gap tracking. | Update status/owner columns weekly. | Generated 2026-05-19
Main Chapter 3 correction | Old thesis text still says Express/MySQL/Python/AWS | Current project is React + Vite, Hono API, Neon Postgres, Cloudflare-targeted Worker path, TypeScript DSS engine. | Rewrite architecture and methodology sections. | backend/src/honoLocalApp.ts; backend/src/services/dssEngine.ts; docs/clothcycle-current-erd.dbml
DSS strength | Implemented beyond simple IF-THEN | Current DSS has eligibility gates, weighted scoring, burn-test confidence, preference boost, buyback add-on, audit trail. | Reflect this in Chapter 3 and appendices. | docs/dss-matrix.md; ClothCycle_DSS_QA_Test_Cases.xlsx
ERD | Updated from live Neon schema | DBML now includes recovery codes, schema migrations, auth/audit fields, simplified transaction statuses. | Generate fresh ERD online from docs/clothcycle-current-erd.dbml. | docs/clothcycle-current-erd.dbml
Feature risk | Some thesis claims need softening | Separate Super Admin, live DB-driven DSS rules, full map API, and audited impact estimates are not fully implemented. | Either implement later or revise claims. | Feature Gap Tracker sheet
Citation risk | Needs exact bibliography cross-check | The tracker maps citation needs to current DSS claims, but final references should match the thesis bibliography. | Verify reference numbers in final manuscript. | DSS Evidence Citations sheet
Suggested commit message | docs: align thesis tracker and ERD with current DSS implementation | Short enough for git and clear for groupmates. | Use after reviewing generated files. | N/A

## Chapter 3 Changes
ID | Chapter/Section | Current Thesis Text / Claim | Current Project Reality | Required Change | Priority | Status | Evidence / File | Citation Need | Owner | Notes
CH3-001 | System Architecture | AWS-hosted setup with React, Node.js/Express, MySQL, Python DSS module. | React + Vite frontend, Hono backend, Neon Postgres for QA, Cloudflare Worker target, TypeScript DSS module. | Rewrite full architecture paragraph and Figure 8 labels. | Critical | To Do | backend/src/honoLocalApp.ts; backend/src/worker.ts; docs/cloudflare-hono-d1-deploy.md | Cloudflare/Hono and Neon architecture citations if external claims are used.
CH3-002 | Use Case Actors | Donor, Partner Organization (Admin), Super Admin. | Actual roles are user, partner, admin. No separate super_admin role currently exists. | Rename actors or implement separate super_admin before claiming it. | High | To Do | src/routes.jsx; src/app/components/ProtectedRoute.jsx | Role-based access control citation optional.
CH3-003 | DSS Engine Design | Python DSS module integrated through RESTful API. | DSS is TypeScript service inside backend: buildPathwayRecommendations and analyzeBurnTest. | Replace Python module references with TypeScript backend service. | Critical | To Do | backend/src/services/dssEngine.ts | Knowledge-driven DSS; rule-based DSS; explainable recommendation citations.
CH3-004 | Database | MySQL tables: users, submissions, partners, tracking, buyback_requests. | Live Neon Postgres has 25+ tables including recommendation_runs/results, messages, notifications, auth_events, transactions. | Replace MySQL table list with current ERD summary. | Critical | Done in docs DBML | docs/clothcycle-current-erd.dbml | PostgreSQL/Neon only if explaining deployment tech.
CH3-005 | Partner Coordination | Users submit request summaries externally through existing channels. | Current system sends briefs in-app to partners, creates transactions, messages, and notifications. | Revise to in-platform partner handoff with partner decision workflow. | High | To Do | backend/src/controllers/dssController.ts; src/app/pages/PartnerDashboard.jsx | Platform coordination / traceability citations.
CH3-006 | Tracking | Primarily user-reported status tracking. | Current flow includes partner/admin status updates; user sees request history and status. | Clarify status authority: user sees history; partner/admin update request statuses. | High | To Do | src/app/pages/SubmittedRequestsPage.jsx; backend/src/controllers/dssController.ts | Traceability/accountability citation.
CH3-007 | DSS Output | Recommendation, concise justification, guidance. | Outputs include all ranked pathways, confidence, score, matched/missed checks, burn-test result, and audit payload. | Expand DSS output description. | High | To Do | docs/dss-matrix.md | Explainable DSS / transparency citation.
CH3-008 | Burn Test | Maps to Natural, Synthetic, Mixed Blend, Unknown. | Actual burn test ranks top 3 fibers: cotton, linen, rayon/tencel, silk, wool, nylon, polyester/poly fleece, acetate, acrylic, spandex. | Replace broad mapping with current top-3 confidence approach. | High | To Do | backend/src/services/dssEngine.ts | Textile burn-test/fiber identification source needed.
CH3-009 | Business Rules | R001-R011 IF-THEN rules and highest-priority fully satisfied pathway. | Actual DSS uses hard gates plus weighted scoring and +8 preference boost. | Update BRS appendix and methodology explanation. | Critical | To Do | docs/dss-matrix.md | Circular economy prioritization and multi-criteria decision support citations.
CH3-010 | Buyback | Upcycling with buyback when item meets encoded criteria. | Current code adds buyback when buyback_interest=true with fixed score 78; does not deeply re-evaluate partner pricing/production feasibility. | Describe buyback as add-on interest/request route, not guaranteed eligibility/pricing. | High | To Do | backend/src/services/dssEngine.ts | Upcycling/buyback/circular business model citation.
CH3-011 | GIS/Maps | GIS/Maps API and mapped nearby facilities. | Current system has coordinate-based partner ranking and visual plotted map; full external map API may not be production-grade. | Phrase as partner discovery with location ranking unless full Maps API is finalized. | Medium | To Do | backend/src/services/gisService.ts; src/app/pages/DssConfirmationPage.jsx | GIS/location-based service citation.
CH3-012 | Operations | Hosted on university server/academic cloud. | Current target is Cloudflare-compatible Hono deployment with Neon Postgres; local testing on localhost:5000. | Update staging/deployment wording. | High | To Do | backend/wrangler.toml; docs/wrangler-docker-wrapper.md | Cloud deployment citation optional.
CH3-013 | Privacy | No PII beyond user contact for buyback notifications. | System stores account profile data, phone/address, profile photos, messages, notifications, auth events. | Revise privacy and delimitations to match actual data collection. | Critical | To Do | docs/clothcycle-current-erd.dbml; src/app/pages/LegalDocumentPage.jsx | RA 10173/Data Privacy Act citation.
CH3-014 | Testing Instruments | SUS, PSSUQ, UEQ-S, TAM, AttrakDiff. | App has technical QA workbook and test file; usability instruments are thesis execution tasks, not code features. | Keep as research method, add DSS QA test cases as technical validation artifact. | Medium | To Do | ClothCycle_DSS_QA_Test_Cases.xlsx; backend/src/services/dssEngine.test.ts | SUS/PSSUQ/UEQ/TAM source citations.

## Feature Gap Tracker
ID | Feature / Claim | Implemented Now? | Current Implementation | Gap / Risk | Recommended Action | Priority | Status | Evidence / File | Notes
GAP-001 | User register/login/logout | Yes | Email/password, Google login, 2FA, reset password. | Need continue smoke testing after route guard/session changes. | Keep in scope. | High | Implemented / Test | src/context/AuthContext.tsx; backend/src/controllers/authController.ts
GAP-002 | Role guards | Mostly yes | ProtectedRoute blocks user/partner/admin paths on frontend; backend endpoints check auth/admin in many controllers. | Some generic submission status endpoints may need stricter ownership/role checks. | Audit status update endpoints before QA. | High | Review | src/app/components/ProtectedRoute.jsx; backend/src/controllers/submissionController.ts
GAP-003 | Textile item submission | Yes | Multi-step form saves submission, details, burn test, images. | Image upload depends on local uploads or R2 config. | Document upload limitations and QA test image upload. | High | Implemented / Test | src/app/pages/SubmissionFormPage.jsx; backend/src/controllers/submissionController.ts
GAP-004 | DSS Recycle/Donate/Upcycle/Buyback/Rejected | Yes | Weighted scoring and eligibility gates. | Thesis still describes simpler flow. | Update thesis and appendices. | Critical | Implemented | backend/src/services/dssEngine.ts; docs/dss-matrix.md
GAP-005 | User view submission history/status | Yes | User dashboard and Submitted Requests page. | Charts/impact should be described as operational metrics, not audited sustainability impact. | Revise impact wording. | Medium | Implemented / Test | src/app/pages/UserDashboard.jsx; src/app/pages/SubmittedRequestsPage.jsx
GAP-006 | Partner view/manage assigned requests | Yes | Partner dashboard lists requests, modal, status decision. | Need QA for own-message view routing and modal image behavior. | Test before defense. | High | Implemented / Test | src/app/pages/PartnerDashboard.jsx
GAP-007 | Partner preferences require admin approval | Partial yes | Partner rule change request workflow exists. | Does not automatically rewrite live DSS rules or partner matching logic yet. | Phrase as admin-reviewed partner rule/preference requests. | High | Implemented / Clarify | backend/src/controllers/dssController.ts
GAP-008 | Admin approve/decline partner preferences | Yes | Admin can update partner rule request status and notify partner. | UI quality and exact statuses should be tested. | Keep and test. | High | Implemented / Test | src/app/pages/AdminDashboard.jsx; backend/src/controllers/dssController.ts
GAP-009 | Admin manage users | Yes | Admin user CRUD endpoints and UI. | Need smoke test delete/suspend/edit roles. | Test before QA. | High | Implemented / Test | backend/src/controllers/adminController.ts
GAP-010 | Admin manage submissions | Partial | Admin can list and update submission statuses. | Not a full rich submission management module. | Either implement more or word as status oversight. | Medium | Partial | backend/src/controllers/adminController.ts
GAP-011 | Admin manage DSS rules | Partial | CRUD table exists for dss_rules. | Actual engine still reads hardcoded TypeScript rules, not DB rules. | Do not claim live rule editing unless implemented. | Critical | Partial | backend/src/controllers/adminController.ts; backend/src/services/dssEngine.ts
GAP-012 | Audit logs for admin actions | Partial | activity_logs used for admin submission status; recommendation audit exists. | Not every admin action has an activity_log row. | Add logs or soften claim. | Medium | Partial | backend/src/controllers/adminController.ts; docs/clothcycle-current-erd.dbml
GAP-013 | GIS partner map | Partial | Coordinate ranking and custom plotted map. | No full map provider confirmed. | Describe accurately or integrate full map API. | Medium | Partial | backend/src/services/gisService.ts
GAP-014 | Download/copy request summary | Partial | Partner brief is sent in-app; admin DSS CSV export exists. | User download/copy of partner brief may be missing. | Add UI or revise thesis. | Low | Backlog | src/app/pages/DssConfirmationPage.jsx
GAP-015 | Separate Super Admin | No | Only admin role. | Thesis says Super Admin. | Remove Super Admin wording or add role. | High | To Decide | src/routes.jsx
GAP-016 | Impact dashboard | Partial | Charts from submissions/request data. | Not validated textile diversion estimates. | Use as engagement/status metrics. | Medium | Clarify | src/app/pages/UserDashboard.jsx; src/app/pages/AdminDashboard.jsx

## DSS Evidence Citations
ID | DSS Claim / Evidence Need | Current Implementation | Where Used in Thesis | Recommended Citation Topic | Current File Evidence | Citation Status | Notes
DSS-CIT-001 | Knowledge-driven DSS is appropriate for consumer textile routing. | Rule-based backend DSS evaluates user-submitted textile criteria. | Chapter 1/2 rationale; Chapter 3 methodology. | Knowledge-driven DSS; explainable rule-based DSS. | backend/src/services/dssEngine.ts | Needs exact bibliography number | Use your existing DSS literature refs, likely Chapter 1/2 DSS sources.
DSS-CIT-002 | Circular economy pathways include donation/reuse, recycling, and upcycling. | Pathways are recycle, donate, upcycle, buyback add-on, rejected gate. | Scope and DSS process flow. | Circular economy textile lifecycle and end-of-life pathways. | docs/dss-matrix.md | Needs exact bibliography number
DSS-CIT-003 | Fiber composition affects textile recovery feasibility. | Material/fiber scoring distinguishes cotton/natural, polyester/synthetic, blends, wool/silk. | Rule base rationale. | Textile recycling feasibility by fiber composition. | backend/src/services/dssEngine.ts | Needs exact bibliography number
DSS-CIT-004 | Condition and cleanliness affect donation eligibility. | Donation gates block heavily damaged, heavily soiled, restricted/uniform items. | Donation rule section. | Donation hygiene/redistribution suitability; circular reuse quality criteria. | backend/src/services/dssEngine.ts | Needs source
DSS-CIT-005 | Burn test helps identify fabric behavior. | Burn test ranks top 3 possible fibers with partial scoring. | Burn test guidance/design. | Textile burn test/fiber identification reference. | backend/src/services/dssEngine.ts; backend/src/services/dssEngine.test.ts | Needs source | Important for defense because burn test is a visible DSS feature.
DSS-CIT-006 | Explainability improves trust in DSS recommendations. | UI shows confidence, matched/missed checks, why-this-was-recommended accordion. | DSS output surface and transparency requirement. | Explainable DSS / transparent recommender systems. | src/app/pages/DssConfirmationPage.jsx; docs/dss-matrix.md | Needs exact bibliography number
DSS-CIT-007 | GIS/location supports actionable disposal decisions. | Partner discovery ranks/filters by pathway, coordinates, distance. | GIS component and partner directory. | GIS/location-based sustainability services. | backend/src/services/gisService.ts | Needs exact bibliography number
DSS-CIT-008 | Buyback/upcycling supports circular value recovery but acceptance is external. | Buyback is an add-on recommendation at fixed score 78 when user selects buyback interest. | Buyback scope/delimitation. | Upcycling, circular business models, buyback/take-back programs. | backend/src/services/dssEngine.ts | Needs source | Do not claim guaranteed pricing.
DSS-CIT-009 | Audit trail supports DSS validation and thesis defense. | recommendation_runs and recommendation_results store engine_version, input_snapshot, output_payload. | Testing/audit/admin methodology. | DSS validation, traceability, auditability. | backend/src/controllers/dssController.ts; docs/clothcycle-current-erd.dbml | Project evidence enough; external source optional
DSS-CIT-010 | User-selected pathway may differ from DSS top recommendation. | UI separates DSS cards from pathway selector and requires confirmation on mismatch. | DSS user control and transparency. | Human-in-the-loop decision support / user autonomy. | src/app/pages/DssConfirmationPage.jsx | Needs source if emphasized

## ERD Database Tracker
ID | ERD / DB Area | Current Live Schema | Thesis/Docs Update Needed | Status | Priority | Evidence | Notes
DB-001 | Database platform | Neon PostgreSQL current QA schema. | Replace MySQL references. | Done in DBML | Critical | docs/clothcycle-current-erd.dbml
DB-002 | Authentication | users, password_reset_tokens, user_recovery_codes, auth_events, rate_limits. | Show auth/security tables in ERD if space allows. | Done in DBML | High | Live Neon schema
DB-003 | Submission intake | submissions, submission_details, burn_tests, submission_images. | Replace generic textile table with detailed intake entities. | Done in DBML | Critical | docs/clothcycle-current-erd.dbml
DB-004 | DSS audit | recommendation_runs, recommendation_results, recommendation_feedback, dss_rules. | Add DSS audit trail to methodology and ERD. | Done in DBML | Critical | backend/src/controllers/dssController.ts
DB-005 | Partner handoff | transactions with statuses pending, accepted, completed, rejected. | Update status list and request lifecycle. | Done in DBML | High | backend/src/db/migrations/021_simplify_dss_request_statuses.sql
DB-006 | Messages/notifications | messages, conversations, message_attachments, notifications. | Add communication module to ERD/system architecture. | Done in DBML | High | docs/clothcycle-current-erd.dbml
DB-007 | Partner preferences | partner_rule_change_requests plus partner capacity/preference columns. | Add admin-reviewed partner preference workflow. | Done in DBML | Medium | backend/src/controllers/dssController.ts
DB-008 | Operational logs | activity_logs and schema_migrations. | Mention system logs and migration tracking. | Done in DBML | Medium | Live Neon schema
DB-009 | D1 schema | Still exists as Cloudflare reference, but current QA DB is Neon. | Avoid presenting D1 as current primary DB unless deployed that way. | Done in DBML note | High | backend/src/db/d1-schema.sql; docs/cloudflare-hono-d1-deploy.md

## QA UAT Tracker
ID | QA / UAT Task | Module | Precondition | Expected Evidence | Priority | Status | Artifact / File | Notes
QA-001 | Run existing backend DSS unit tests. | DSS | backend deps installed | Cotton/polyester/wool, donation, restricted category, upcycle, fabric scraps tests pass. | Critical | To Run | backend/src/services/dssEngine.test.ts
QA-002 | Execute generated DSS QA workbook. | DSS | App running with test accounts | Actual Result and Pass/Fail columns completed. | Critical | To Do | ClothCycle_DSS_QA_Test_Cases.xlsx
QA-003 | Submit textile with images. | Submission | Backend local uploads/R2 path configured | Images upload, labels persist, partner/user view carousel works. | High | To Test | src/app/components/ImageCarousel.jsx
QA-004 | Route guard direct URL test after logout. | Auth/RBAC | Logged out state | /dashboard, /partner, /admin redirect to login. | Critical | To Test | src/app/components/ProtectedRoute.jsx
QA-005 | Partner request accept/reject/completed. | Partner | Pending transaction exists | User receives message and notification; status updates. | High | To Test | src/app/pages/PartnerDashboard.jsx
QA-006 | Admin partner rule request review. | Admin | Partner submitted request | Admin note/status sends partner message/notification. | High | To Test | src/app/pages/AdminDashboard.jsx
QA-007 | DSS audit export. | Admin | Recommendation runs exist | CSV downloads with engine_version and matched/missed rules. | Medium | To Test | backend/src/controllers/dssController.ts
QA-008 | Settings profile/photo/password/account delete. | Settings | Role-specific account logged in | Profile saves to DB; photo respects upload limits; password validation shown on focus; delete account works. | High | To Test | src/app/pages/SettingsPage.jsx
QA-009 | User dashboard charts and status cards. | Dashboard | Submissions and requests exist | Counts/charts match actual records. | Medium | To Test | src/app/pages/UserDashboard.jsx
QA-010 | Forgot password code-first flow. | Auth | Email provider/dev code available | Code verification precedes new password fields. | High | To Test | src/app/pages/LoginPage.jsx

## Cloudflare Hono
ID | Deployment Concern | Current Project Reality | Risk | Required Action | Priority | Status | Evidence / File
DEP-001 | Cloudflare target | Hono Worker exists in backend/src/worker.ts; local Hono app uses Neon/Node. | Two backend paths can drift. | Keep Worker and local API route behavior aligned. | High | Monitor | backend/src/worker.ts; backend/src/honoLocalApp.ts
DEP-002 | Database choice | Current QA uses Neon Postgres; Worker D1 services still exist. | Thesis/deployment docs can confuse Neon vs D1. | State Neon current QA clearly; D1 as reference unless final deployment uses it. | High | Updated in DBML | docs/clothcycle-current-erd.dbml
DEP-003 | Uploads | Local Hono can write uploads folder in development; Worker path should use R2. | Local disk won't work on Cloudflare Workers. | Use R2 for production uploads. | Critical | Backlog | backend/src/controllers/uploadController.ts; backend/src/services/r2Service.ts
DEP-004 | Node-only modules | Local Hono app imports node:fs/path for local uploads. | Not Worker-compatible, but okay for local Node app. | Do not deploy honoLocalApp.ts as Worker entry. | High | Document | backend/src/honoLocalApp.ts
DEP-005 | Env/secrets | DATABASE_URL, JWT_SECRET, TWO_FACTOR_ENCRYPTION_KEY, CORS origins, R2/email/Google vars. | Missing secrets break auth/uploads/email. | Finalize .env.example and Wrangler secrets before deploy. | High | To Do | backend/.env.example; backend/wrangler.toml
DEP-006 | Connection pooling | Node local uses pg Pool against Neon. | Serverless Worker should use Worker-compatible DB approach or D1 path. | Decide final production data path before deployment freeze. | Critical | Decision Needed | backend/src/config/database.ts; backend/src/config/d1.ts
DEP-007 | Frontend API URL | Frontend uses VITE_API_URL. | Wrong URL breaks all API calls after deployment. | Set VITE_API_URL to deployed API. | High | To Do | src/services/api.ts; .env.example
DEP-008 | Bundle size | Vite build may warn due dashboard/page imports. | Slow loading but not thesis blocker. | Keep lazy routes; code split if warning becomes severe. | Low | Backlog | src/routes.jsx

## General Reminders
Reminder | Why It Matters | Action | Priority | Status
Do not claim Python DSS anymore. | It is factually wrong for current code. | Replace with TypeScript/Hono backend DSS engine. | Critical | To Do
Do not claim MySQL anymore. | ERD and live DB are Neon PostgreSQL. | Use updated DBML. | Critical | Done in docs
Be careful with Super Admin wording. | No separate role exists. | Use Admin or implement super_admin. | High | To Decide
Do not overclaim impact reduction. | Current charts are operational/engagement metrics. | Say preliminary indicators, not audited waste diversion. | High | To Do
DSS is the star. | Defense will likely inspect rule logic. | Bring dss-matrix.md, DSS QA workbook, and audit export. | Critical | To Prepare
Validate citations before final print. | Tracker maps citation needs but not exact bibliography numbering. | Cross-check Word references. | High | To Do
Keep partner acceptance external-limited. | Partners decide capacity/pricing/logistics. | Phrase platform as coordination and decision support. | High | To Do
Generate ERD from DBML after every schema change. | Docs and defense diagrams must match DB. | Use docs/clothcycle-current-erd.dbml. | Medium | Ongoing